Meeting Minutes #

DATE: March 4 2025

TIME: 60 mins

LOCATION: 1A18

| Meeting called by | Bashu |
| --- | --- |
| Type of meeting | Biweekly Meeting |
| Minutes taken by | Sara |
| List of attendees | Bashu, Sara, Parvaneh, Asutosh, Anukul |
| List of absentees | N/A |
| Excuses |  |
| Agenda | - Update and planning of E3MT 2025 competition |
| Content | - Operations – Prior to Event - Order 3 large coffee and gift cards from Tims (Bashu) - 35 of $10 - 6 of $20 - Prepare all certificates with the frames (Parvaneh & Sara) - Grab mugs, bags from the bookstore day before the event (Parvaneh & Anukul) - Print executives name for nameplate (Anukul) - Contact with the host (Sara) - Update handbook with agenda (Sara) - Contact to Mike for the projector 1 day before (Bashu) - Judging spreadsheet - Judges will email Asutosh their completed spreadsheets - Create separate spreadsheet to sum totals (Asutosh) - SWAG Gift assembling on the morning of the event (All executives) - Got 29 pairs of socks from Lori for participants - Email to Judges (Asutosh) - Map - Parking arrangements - Handbook - Rubric (state they need to bring a laptop) - Email to Keynote Speakers (Bashu) - Map - Parking arrangements - Agenda - Email to Participants (Sara) - Handbook with agenda - Email to faculty and students (Sara) - Formal invite - Handbook - Compilation of powerpoints (Anukul) - Printing of pages saying Library is reserved (Sara) - Place on tables on Friday - Handover of certificates, prizes to speakers, judges and winners by Dr. Soltan and Bashu - Operations – Day of - Set up/take down – all executives be there (9am) - Get cart from Deans office - Get the projector from Mike (Bashu) - MC – Kiranbir Kaur - Print the agenda (Sara) - Pick up people from parking (Parvaneh) - Masterslide control (Anukul will bring laptop) - Receive Pizza (Asutosh) - Photos – Volunteer (Gopesh) - Counting judges' votes (Asutosh & Sara) - Write winners name on the certificate - Registration (Asutosh & Sara) - Printing of participants name for their signature (Sara) |
|  | Next Meeting: Friday, March 7 at 9 am in the library |